# NOTES AND GUIDANCE															v1.01 – 27 October 2002

# Colour Coding

Completed tasks are shown in BLUE.

Tasks which are on plan are shown in GREEN

Tasks which are now critical or late are shown in RED.

Tasks which are overdue but reallocated

# Priority Coding

Important tasks are shown in bold text.

Normal tasks are shown in plain text.

Tasks which do not (yet) have a specific target date, but are included indicatively on the plan for completeness, are shown in italics.

# Convention Coding

Conventions are annotated as follows.

A   	means Agent Attending

D	means Con Desk being run

P	means Programme Item or Party (or both)

# Level of Detail

This high level plan operates at monthly granularity and covers the 3 years until Interaction.

Additional plans will be produced at lower levels of granularity later.  It is expected that a plan to the weekly level will be

required from no later than Easter 2005 (maybe even New Year 2005), a daily plan for the last 4-6 weeks before the con,

and an hourly plan for the con and a few days either side.

# General

To keep the data volume manageable, in most cases the timeline does not show every “ripple” of every decision.

For instance, it is implicit that whenever a PR comes out, it will be made available on the website – but putting an entry in the website

timeline for every PR just to say that this is done would make the timeline unwieldy. Exceptions to this rule are made where

the “ripple” activities are themselves significant or need a lot of effort.

# YEAR 1 – CONJOSE to TORCON III																					v1.01 – 27 October 2002

| Area | Cons | Meetings | Finance | Office & Member Admin | Staff Services | Site & Facilities | Pubs (Int. & Ext.) | Website | Promotions & Press | WSFS | Programme Inc GoH, Art, Dealers | Other |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sep 2002 | 1 Conjose (ADP) |  |  |  |  |  |  | Add Site Search | Earthlight Ad. Deal. |  |  |  |
| Oct 2002 |  |  | Business Plan for Bank. | Complete initial member DB |  | Review Infotel Contract. |  |  |  |  | GoH Contact (Glasgow Win) |  |
| Nov 2002 | 1-3 Novacon 32 (ADP) | Board (@ Novacon) | Credit Card Facility |  |  | Sign Infotel Contract | PR0 mailout. New Fliers Sailing The Clyde | Online CoA Online Member DB | PressRel – Infotel |  | Confirm Conference details with Farah. |  |
| Dec 2002 |  | Board IRC | Sign Subvention Agreement . |  |  | Sign SECC & Key Hotel Contracts. | Stationery design. Advert rate card. | Online Volunteers Online Reg. Sales. | Con. Merchandise supplier contracted. |  |  |  |
| Jan 2003 |  |  |  | Register with Electrical Eggs. | Recruit volunteer coordinator |  | Select PR / Souvenir Book Artist Sailing The Clyde |  |  |  |  |  |
| Feb 2003 | 21-23 Redemption (AP) | Board IRC |  | Approve Rate Increase |  |  | Publicise Rate Increase | Publicise Rate Increase | PressRel - Rates |  |  |  |
| Mar 2003 |  |  |  |  |  |  | Ext. Newsletter ? Sailing The Clyde |  | . |  |  |  |
| Apr 2003 | 18-21 Seacon (ADP) | Board (@ Seacon) | Budget baselined | Rate Increase |  |  | Fix pubs timeline. |  | Con. Merchandise available |  |  |  |
| May 2003 |  |  |  |  |  |  | Sailing The Clyde |  |  |  |  |  |
| Jun 2003 |  | Board IRC |  |  |  |  |  |  |  |  |  |  |
| Jul 2003 |  |  |  | Approve Rate Increase | Construction Staff Weekend. |  | Publicise Rate Increase Sailing The Clyde | Publicise Rate Increase | PressRel - Rates |  |  |  |
| Aug 2003 | 28-1 Torcon (ADP) | Board (@ Torcon) |  |  |  |  | PR1 Issued |  |  |  |  |  |

# YEAR 2 – TORCON III to NOREASCON 4																				v1.01 – 27 October 2002

| Area | Cons | Meetings | Finance | Office & Member Admin | Staff Services | Site & Facilities | Pubs (Int. & Ext.) | Website | Promotions & Press | WSFS | Programme Inc GoH | Other |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sep 2003 | 1 Torcon (ADP) |  |  | Rate Increase |  |  | Sailing The Clyde |  |  |  | Artshow and Dealer Coord. Appointments |  |
| Oct 2003 |  | Board IRC |  |  |  |  |  |  |  |  |  |  |
| Nov 2003 | Novacon 33 |  |  |  |  |  | Sailing The Clyde |  |  |  |  |  |
| Dec 2003 |  | Board IRC |  |  |  |  |  |  |  |  |  |  |
| Jan 2004 |  |  |  |  |  |  | Sailing The Clyde |  |  |  | Programme team initial recruitments |  |
| Feb 2004 |  | Board IRC |  | Approve Rate Increase |  |  | Publicise Rate Increase | Publicise Rate Increase | PressRel - Rates |  |  |  |
| Mar 2004 |  |  |  |  |  |  | Sailing The Clyde |  |  |  | Plan N4 Closing Ceremony / Hugo losers party |  |
| Apr 2004 | 9-12 Concourse (ADP) | Board (@ Concourse) |  | Rate Increase |  | Accomm. Website in development. | Ext. Newsletter ? |  |  |  | Artshow & Dealer Bookings Open |  |
| May 2004 |  |  |  |  |  |  | Sailing The Clyde |  |  |  |  |  |
| Jun 2004 |  | Board IRC |  |  | Staff Weekend ? |  |  |  |  |  |  |  |
| Jul 2004 |  |  |  | Approve Rate Increase |  |  | Publicise Rate Increase Sailing The Clyde | Publicise Rate Increase | PressRel - Rates |  |  |  |
| Aug 2004 |  |  |  |  |  |  |  |  |  |  |  |  |

# YEAR 3 – NOREASCON 4 to INTERACTION																				v1.01 – 27 October 2002

| Area | Cons | Meetings | Finance | Office & Member Admin | Staff Services | Site & Facilities | Pubs (Int. & Ext.) | Website | Promotions & Press | WSFS | Programme Inc GoH | Other |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sep 2004 | 2-6 Noreascon (ADP) | Board (@ N4) |  | Rate Increase | Child Care Appoint. | Accommodation bookings start. | PR2 Issued Sailing The Clyde |  | Initial Contacts with TV / Radio ? | Site Selection, Hugo Admin, Business Meeting appointments | Run Closing Ceremony, Hugo Losers Party. |  |
| Oct 2004 |  | 2nd-3rd Construction 3 staff weekend |  |  |  |  | Appoint Editors for Souvenir Book, Readme, Restaurant Guide. |  |  |  |  |  |
| Nov 2004 | Novacon 34 | Board IRC |  |  |  |  | Sailing The Clyde |  |  |  |  |  |
| Dec 2004 |  |  |  |  |  |  | Sailing The Clyde |  |  |  |  |  |
| Jan 2005 |  | Board IRC |  |  | Info Desk Appoint. | Ops Manual drafting starts. | Sailing The Clyde |  |  |  | COPUS Liaison ? |  |
| Feb 2005 |  | Board IRC |  | Approve Rate Increase | Staff Weekend ? |  | Publicise Rate Increase Sailing The Clyde | Publicise Rate Increase | PressRel - Rates |  |  |  |
| Mar 2005 |  | Board IRC |  |  |  | Establish Logistics procedures & Kit List. | Sailing The Clyde |  |  |  |  |  |
| Apr 2005 | Eastercon (ADP) | Board IRC |  | Rate Increase |  |  | PR 3 Issued Sailing The Clyde |  |  |  |  |  |
| May 2005 |  | Board IRC |  |  | Staff Weekend ? |  | Sailing The Clyde |  |  |  |  |  |
| Jun 2005 |  | Board IRC |  |  |  |  | PR4 Issued Sailing The Clyde |  |  |  | Programme final confirmations. |  |
| Jul 2005 |  | Board IRC |  |  |  |  | Sailing The Clyde |  |  |  |  |  |
| Aug 2005 | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION | 4-8 INTERACTION |